# DAWAI

Project Scope Statement, WBS & WBS Dictionary

Project Manager: Mostafa Anwar
Project Sponsor: Ministry of Health
Project Budget: 30,000 L.E.

# Part 1: Project Scope Statement

Project scope statement defines the deliverables, boundaries, and work required to complete the Dawai project. Dawai is planned as a mobile application, not a website. The following scope is a proposed initial version based on the project idea; features not yet confirmed by the project stakeholders should be approved before implementation.

## 1. Product Scope Description

Dawai is a mobile application intended to help users search for medicines and find participating pharmacies that report whether a medicine is available. The app will display relevant pharmacy information, contact details, and the time of the latest availability update when provided. A backend service will process requests and manage medicine and pharmacy data stored in a database. Pharmacy availability depends on updates submitted by participating pharmacies.

## 2. Product Acceptance Criteria

The mobile application can be installed and opened on the agreed target platform(s).

Users can search for a medicine by its name and receive matching results from the system database.

Search results can display participating pharmacies and their reported availability, where data has been entered.

The application displays pharmacy contact/location information and the latest availability update when available.

Authorized staff or pharmacy users can add or update medicine availability through the agreed interface.

The mobile app communicates successfully with the backend, and the backend reads and updates the database correctly.

Core functions pass agreed functional tests, and no unresolved critical defects remain at acceptance.

The project documentation and final demonstration are delivered to the project stakeholder.

## 3. Project Deliverables

Mobile application for medicine search and viewing reported availability.

Backend/API to manage search requests and medicine/pharmacy information.

Database structure for medicines, pharmacies, availability status, and update timestamps.

Agreed interface for authorized pharmacy/staff users to update availability.

Basic test cases and test results.

Project documentation and final demonstration.

## 4. Project Exclusions

A public website or web-based customer application.

Medical diagnosis, treatment recommendations, or prescribing medicines.

Automatic recommendation or substitution of one medicine for another.

Guaranteed real-time stock accuracy unless pharmacies keep availability updated.

Online medicine purchasing, payment processing, and delivery services in the initial version.

Integration with pharmacy inventory/POS systems unless separately approved.

## 5. Project Constraints

The planned project budget is 30,000 L.E.

Delivery must follow the schedule agreed by the project team and stakeholder.

The solution is a mobile application with a backend and database; a website is not included.

Availability information depends on participating pharmacies providing updates.

The project team, available tools, and hosting resources may limit the scope of the initial version.

## 6. Project Assumptions

Participating pharmacies will provide and maintain medicine availability information.

The project team will have access to the required development tools and testing devices.

A suitable hosting environment and database can be used within the project budget.

The project stakeholder will review and approve the requirements and acceptance criteria.

The target mobile platform(s), account types, and exact pharmacy update workflow will be confirmed during requirements review.

# Part 2: Work Breakdown Structure (WBS)

The WBS decomposes the project deliverables into manageable work packages. The numbering below is a proposed code of accounts. The smallest work packages should be planned and estimated according to the course's 8/80 guidance where applicable.

| WBS Code | Work Package / Deliverable | Responsible Person / Role |
| --- | --- | --- |
| 1.0 | Dawai Mobile Application Project | Project Manager |
| 1.1 | Project Planning and Requirements | Project Manager / Team |
| 1.1.1 | Confirm project goals, users, and boundaries | Project Manager |
| 1.1.2 | Collect and document functional requirements | Project Manager / Team |
| 1.1.3 | Approve scope and acceptance criteria | Project Sponsor / Stakeholder |
| 1.2 | System Design | Design / Development Team |
| 1.2.1 | Design mobile app screens and user flow | Mobile Developer / Designer |
| 1.2.2 | Design backend API structure | Backend Developer |
| 1.2.3 | Design database entities and relationships | Backend Developer |
| 1.3 | Mobile Application Development | Mobile Developer |
| 1.3.1 | Implement medicine search interface | Mobile Developer |
| 1.3.2 | Implement pharmacy results and details screens | Mobile Developer |
| 1.3.3 | Implement availability display and update timestamp | Mobile Developer |
| 1.4 | Backend and Database Development | Backend Developer |
| 1.4.1 | Create medicine and pharmacy data models | Backend Developer |
| 1.4.2 | Implement medicine search API | Backend Developer |
| 1.4.3 | Implement availability create/update API | Backend Developer |
| 1.4.4 | Configure database and access permissions | Backend Developer |
| 1.5 | Integration and Testing | Tester / Development Team |
| 1.5.1 | Connect mobile app to backend APIs | Mobile / Backend Developers |
| 1.5.2 | Test medicine search and pharmacy results | Tester |
| 1.5.3 | Test availability updates and data handling | Tester / Backend Developer |
| 1.5.4 | Fix defects and perform regression testing | Development Team |
| 1.6 | Delivery and Documentation | Project Manager / Team |
| 1.6.1 | Prepare user and technical documentation | Project Team |
| 1.6.2 | Prepare final demonstration | Project Team |
| 1.6.3 | Obtain stakeholder acceptance and close project | Project Manager / Sponsor |

# Part 3: WBS Dictionary

The dictionary describes the work packages, responsibility, resources, estimated cost, acceptance criteria, and milestone. Because no detailed schedule or task-level budget was provided, costs and milestones below are planning estimates and must be confirmed by the project team.

| Code | Work Package | Responsible | Resources | Estimated Cost | Acceptance Criteria | Milestone |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1.1 | Confirm goals, users, and boundaries | Project Manager | Stakeholder input, project documents | 1,000 L.E. | Goals, intended users, and exclusions documented and reviewed. | Requirements review |
| 1.1.2 | Document functional requirements | Project Manager / Team | Interviews/meetings, requirements template | 1,500 L.E. | Requirements for user search and pharmacy updates documented. | Requirements review |
| 1.1.3 | Approve scope and acceptance criteria | Project Sponsor / Stakeholder | Scope statement, acceptance checklist | 500 L.E. | Scope and acceptance criteria reviewed and approved. | Scope approval |
| 1.2.1 | Design mobile app screens and flow | Mobile Developer / Designer | Design software, sample devices | 2,500 L.E. | Main screens and user flow reviewed. | Design review |
| 1.2.2 | Design backend API | Backend Developer | API design tools, requirements | 1,500 L.E. | API endpoints and request/response formats documented. | Design review |
| 1.2.3 | Design database | Backend Developer | Database design tool | 1,500 L.E. | Medicine, pharmacy, and availability entities/relationships documented. | Design review |
| 1.3.1 | Build medicine search interface | Mobile Developer | Development computer, mobile framework | 3,000 L.E. | User can enter a medicine name and submit a search. | App feature review |
| 1.3.2 | Build pharmacy results/details screens | Mobile Developer | Development computer, UI assets | 2,500 L.E. | Results show available pharmacy details based on returned data. | App feature review |
| 1.3.3 | Show availability and update time | Mobile Developer | API connection, test data | 1,500 L.E. | Availability status and update time are shown when supplied by backend. | App feature review |
| 1.4.1 | Create medicine/pharmacy data models | Backend Developer | Backend framework, database | 2,000 L.E. | Models store the required medicine and pharmacy fields. | Backend review |
| 1.4.2 | Implement medicine search API | Backend Developer | Backend framework, test client | 2,000 L.E. | API returns matching medicine/pharmacy data for valid queries. | API test |
| 1.4.3 | Implement availability update API | Backend Developer | Backend framework, authorization rules | 2,000 L.E. | Authorized user can update availability and timestamp. | API test |
| 1.4.4 | Configure database and permissions | Backend Developer | Database service, configuration | 1,500 L.E. | Data persists correctly and access is restricted as agreed. | Database review |
| 1.5.1 | Integrate app and backend | Mobile / Backend Developers | Test device, API environment | 1,500 L.E. | App successfully sends requests and displays backend responses. | Integration test |
| 1.5.2 | Test search and pharmacy results | Tester | Test cases, test data, devices | 1,000 L.E. | Documented test cases pass or defects are recorded. | System test |
| 1.5.3 | Test availability updates | Tester / Backend Developer | Test accounts, test database | 1,000 L.E. | Availability changes and timestamps are correctly reflected. | System test |
| 1.5.4 | Fix defects and regression test | Development Team | Issue tracker, test environment | 1,500 L.E. | Critical defects resolved and affected functions retested. | System test |
| 1.6.1 | Prepare documentation | Project Team | Word processor, technical notes | 1,000 L.E. | Required project and user documentation is complete. | Documentation review |
| 1.6.2 | Prepare final demonstration | Project Team | Test device, demo data | 500 L.E. | Main workflow can be demonstrated end-to-end. | Final demo |
| 1.6.3 | Acceptance and project closure | Project Manager / Sponsor | Acceptance checklist, deliverables | 500 L.E. | Stakeholder reviews deliverables and records acceptance. | Project closure |

Total task-level planning estimate: 30,000 L.E.

Budget note: The above task estimates are preliminary and currently total 30,000 L.E. They should be reviewed against actual team costs, hosting, tools, and the final approved scope before being treated as a baseline.

# Planning Notes / Items to Confirm

Confirm whether the first release targets Android only or both Android and iOS.

Confirm who is allowed to update pharmacy availability and how those accounts are approved.

Confirm whether location/map integration is required or pharmacy address/contact details are sufficient.

Confirm the project schedule and assign actual start/end dates to milestones.

The document assumes a basic initial version and excludes a website, online payments, delivery, diagnosis, and prescribing.